## Sheet1
CITS3200 - Team 43 - Network Maps - Sprint 1
RISK REGISTER
A collation of the risks faced in the development and implementation of our software product
RISK | CATEGORY | L LIKELINESS | S SEVERITY | P PREVENTABILITY | RF RISK FACTOR | PROTECTION
Inaccurate Estimation in planning. The team might over or underestimate the complexity of a particular task and in reality spend a lot more/less time in development, moving the actual completion date of the project from the discussed timeframe. | Project Management | 8 | 5 | 8 | 2.5 | An agile development process warrants regular prototyping, discussion with the client and communcation between team members to move resources and man hours between tasks where required. Organisation and communication are key to maintaining a timeframe.
Scope Variation can occur if the client decides they want changes to be made, or more functionality within the software. The addition or changing of functionality within the solution warrants more tasks than initially planned for, potentially altering the timeframe for completion of the project. | Project Management | 7 | 5 | 6 | 3 | Again, the prototyping/sprint nature of the project warranted by the agile development process gives the team more opportunities to present the solution to the client, in the hope that feedback will only warran small, incrememental changes rather than fundamental and time consuming ones.
User Engagement is important to ensure users adopt the software upon its implementation. Users should find the software easy to use, improve their productivity, and be more effective than competing solutions for the best chance of adoption. If the software isn't used, the project will be considered a failure. | Software Design | 2 | 10 | 8 | 2 | During the development process, the importance of communication with the client is again key. Identifying and tailoring the software to the intended users will result in useful software. Testing, surveys, focus groups, frequent updates and polls are all great methods for acquiring valuable feedback to ensure the end user finds the software useful.
Poor Software Design will negatively affect the user's experience. It can come in multiple forms. Inefficient code will result in a slow, laggy user experience. Bug riddled code will have a similar effect. Hard to read code will be difficult to maintain and fix once implemented. All will negatively affect the effectiveness of the project. | Software Design | 4 | 8 | 9 | 1.5 | Poor software design is usually the result of a rushed timeframe. Regular testing, peer review and setting a clear standard to be expected of project code will all act to improve the quality of software design. Having a strong, bugless and easy to read product on implementation will greatly improve the lifespan of the project as it is easier to maintain.
Lack of Ownership | Legal | 10 | 2 | 5 | 3.5
Inability to Acquire Data | Legal | 4 | 10 | 8 | 3
Team Miscommunication | Project Management
Poor Risk Management