## Sheet1
CITS3200 - Team 43 - Network Maps - Sprint 1
RISK REGISTER
A collation of the risks faced in the development and implementation of our software product
RISK | CATEGORY | L LIKELINESS | S SEVERITY | P PREVENTABILITY | RF RISK FACTOR | PROTECTION
Scope Variation can occur if the client decides they want changes to be made, or more functionality within the software. The addition or changing of functionality within the solution warrants more tasks than initially planned for, potentially altering the timeframe for completion of the project. | Project Management | 7 | 5 | 5 | 3.5 | Again, the prototyping/sprint nature of the project warranted by the agile development process gives the team more opportunities to present the solution to the client, in the hope that feedback will only warrant small, incrememental changes rather than fundamental and time consuming ones.
Inability to Acquire Data required for the project. The network map solution in development is pivotal around regularly obtaining information about research papers in the client's field. Both legal and software restrictions could prevent access to this data on a regular basis, slowing the process of map generation for the duration of the solution's lifespan. | Legal | 4 | 10 | 8 | 3 | Regular contact with the client requesting instruction and access (where required) to the data required from the researcher databases requested. Communication with managers of the database and attainment of legal documents where required to authorise access to the data.
Inaccurate Estimation in planning. The team might over or underestimate the complexity of a particular task and in reality spend a lot more/less time in development, moving the actual completion date of the project from the discussed timeframe. | Project Management | 8 | 5 | 8 | 2.5 | An agile development process warrants regular prototyping, discussion with the client and communcation between team members to move resources and man hours between tasks where required. Organisation and communication are key to maintaining a timeframe.
Lack of Ownership of the project. Without a clear allocation of who is responsible for what, tasks can be left undone and certain areas neglected. Ownership must be stated clearly and early on in the development process to avoid this. | Legal | 10 | 2 | 7 | 2.5 | Initial project considerations must be made to ensure ownership is defined and clear to all parties. In meetings, responsibilities can be set for the client along with the user. Clear communication must be recorded and maintained between the development team and the client for the duration of the project, including but not limited to meeting minutes, actions and legal documents if required.
User Engagement is important to ensure users adopt the software upon its implementation. Users should find the software easy to use, improve their productivity, and be more effective than competing solutions for the best chance of adoption. If the software isn't used, the project will be considered a failure. | Software Design | 2 | 10 | 8 | 2 | During the development process, the importance of communication with the client is again key. Identifying and tailoring the software to the intended users will result in useful software. Testing, surveys, focus groups, frequent updates and polls are all great methods for acquiring valuable feedback to ensure the end user finds the software useful.
Poor Software Design will negatively affect the user's experience. It can come in multiple forms. Inefficient code will result in a slow, laggy user experience. Bug riddled code will have a similar effect. Hard to read code will be difficult to maintain and fix once implemented. All will negatively affect the effectiveness of the project. | Software Design | 4 | 8 | 9 | 1.5 | Poor software design is usually the result of a rushed timeframe. Regular testing, peer review and setting a clear standard to be expected of project code will all act to improve the quality of software design. Having a strong, bugless and easy to read product on implementation will greatly improve the lifespan of the project as it is easier to maintain and improve in future updates.
Team Miscommunication occurs when two developers are not clear with communication and as a result do not optimise the division and development of project tasks. In some cases, developers may even work on the same task simultaneously but seperately, completely wasting a large amount of time valuable if applied elsewhere. | Project Management | 7 | 4 | 8 | 1.5 | Having regular team meetings and allocating tasks and actions will work to prevent miscommunication. Setting up a standard for communication (in our case Discord and Teams) where members are kept up to date with deadlines and new actions will optimise the efficiency of the team development process.
Poor Risk Management can occur when the scope of the project and its tasks are not correctly assessed and so forth mitigated. A plethora of issues can arise from a lack of adequate assessment including legal implications, extra work, and a poor sense of scope. The main effect will be time pressure, requiring the development team to do more work to keep to the time frame that wasn't initially planned for. | Project Management | 3 | 7 | 8 | 1 | An initial understanding of the scope of the project is vital to identify the associated risks brought about by the development process. Defining the risks will be an ongoing process, but it is most important to define a standard for calculating the overall 'risk factor' of a particular risk. Factors contributing to the overall risk include likelihood of occurance, consequence upon occurance, and the preventability of occurance.